## Vista
Prepared by: | vanajakshi
Report Date | 15.09.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142102 | 26.07.2022 | Armored cable | Duplicate sent to MD's approval
142137 | 9.08.2022 | cable tray | Estimation sent to MD'S approval
142152 | 18.08.2022 | Toys & dolls | Promotion to follow up
142183 | 6.09.2022 | PVC Reducer Tee | PO:91820
142186 | 07.09.2022 | LED surface square light | PO:91861
142188 | 07.09.2022 | Gas cylinder | Admini to follow up
List of requisitions Where PO/WO is prepared and items have not received at site
141447 | 05.05.2022 | MS Grills | Pick up from SOV
141903 | 25.05.2022 | MS Grills 3'4' | Pick up from SOV
141964 | 11.06.2022 | Floor tile country almond | Pick up from GMR
142003 | 24.06.2022 | Bathroom wall tiles | Pick up from GMR
142015 | 11.07.2022 | MS Grills | Pick up from SOV
142037 | 04.07.2022 | Floor large tiles | Pick up from GMR
142040 | 04.07.2022 | Malasian brown DK | Pick up from GMR
142051 | 07.07.2022 | Large tiles(Tagus & marbo opera)tiles | Pick up from GMR
142054 | 07.07.2022 | Large tiles | Pick up from GMR
142075 | 15.07.2022 | Creche toys &books | Next week delivery
142087 | 20.07.2022 | Taugs & Marbo opera tiles | Pick up from GMR
142112 | 1.08.2022 | Powder caoted grill | Pick up from SOV
142115 | 02.08.2022 | Guard alert siren | Supplier Arranging material
142125 | 04.08.2022 | Ceramic wall tiles | Pick up from GMR
142159 | 23.08.2022 | SS dust bin | Supplier Arranging material
142160 | 24.08.2022 | SS Name plate | Supplier Arranging material