## MPPL
Prepared by: | Mounika
Report Date | 2022-09-10
Site | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178711 | 10.08.22 | Laptop Adptor | Cancelled
178740 | 29.08.22 | Cement Board | Rates Negonegotiated
178744 | 05.09.22 | Smile play | Quotation
List of requisitions Where PO/WO is prepared and items have not received at site
178127 | 29.01.21 | Wall Hung | Bulk Order
178477 | 31.03.22 | Touhened Glass | Pick from SSLLP
178479 | 05.04.22 | Grills | Pick from SSLLP
178547 | 06.05.22 | Wood Dark tiles | Delivered
178558 | 14.07.22 | Wires | Pick from SSLLP
178578 | 31.05.22 | Panel Doors | Pick from SSLLP
178617 | 24.06.22 | Malasin Tiles | Pick from GMR
178620 | 27.06.22 | Timer & L & T | Delivered
178641 | 09.07.22 | Back Pack | Online purchase
178666 | 20.07.22 | Spring Wire | Pick from Supplier
178670 | 22.07.22 | Timer | Cancelled
178679 | 30.07.22 | Ranger Blue | Pick from GMR
178693 | 02.08.22 | Glass Mosaic Tiles | Pick from Supplier
178706 | 09.08.22 | MS Grills | Pick from SSLLP
178708 | 09.08.22 | Kitchen Cabinate | Work Under Process
178717 | 13.08.22 | Country rosso | Pick from GMR
178720 | 16.08.22 | Plain false ceiling | Follow up with Supplier
178721 | 18.08.22 | Modular plates | Delivered
178722 | 19.08.22 | Chimney-Hindware | Pick from Supplier
178723 | 19.08.22 | UPVC French Door | Follow up with Supplier
178727 | 23.08.22 | CC TV Camera | Pick from SSLLP
178728 | 23.08.22 | Modular plates | Pick from SSLLP
178729 | 23.08.22 | CC TV Camera | Delivered
178733 | 26.08.22 | Maysian Brown DK | Pick from SSLLP
178734 | 26.08.22 | Urbanwood tiles | Pick from GMR
178735 | 26.08.22 | Toughned Glass | Pick from Supplier
178736 | 26.08.22 | CP Sink cock | Delivered
178738 | 29.08.22 | Waste Coupling | Pick from SSLLP
178739 | 29.08.22 | MS Grills | Pick from SSLLP
178741 | 02.09.22 | Main door lights & CCTV | Pick from SSLLP
178743 | 05.09.22 | Tab Brown Granite | Pick from SOV
178746 | 06.09.22 | Malasin Tiles | Pick from GMR
178748 | 06.09.22 | Janatha paste | Delivered
178749 | 07.09.22 | CPVC Pipes | Pick from SSLLP
178750 | 07.09.22 | False ceiling down lights | Delivered
178751 | 07.09.22 | Acid | Delivered