## KNM
Prepared by: | Deepa
Report Date | 15.09.22
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
95188 | 12.08.22 | Floor Tiles | pick up from GMR
95191 | 25.08.22 | consumbles material | pick up from SSLLP
95197 | 03.09.22 | Electrical conducting | pick up from SSLLP
95198 | 06.09.022 | channel bracket | Next weak Delivery
95200 | 06.09.022 | Electrical conducting | pick up from SSLLP
95201 | 06.09.022 | Pvc Door mat | Next weak Delivery