## KNM
Prepared by: | sneha
Report Date | 15.9.22
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165722 | 9.9.22 | Switches items | Po issue 91949
165723 | 9.9.22 | Sanitary | Po issue 91796
165725 | 9.9.22 | Sanitary | Po issue 91797
165726 | 9.9.22 | cp items | Po issue 91783
165727 | 9.9.22 | Switches items | Po issue 91947
List of requisitions Where PO/WO is prepared and items have not received at site
07.5.22
165643 | 07.05.22 | Timer Machines | Cancelled Send me another requisition
165645 | 09.05.22 | Ms gate-v.no.16 | Powder coated not done
165646 | 9.05.22 | Ms gate-v.no.18 | Powder coated not done
165664 | 26.05.22 | Garbage Bin | Next week they will delivery
165688 | 06.07.22 | MS Grill | Powder coated not done
165701 | 2.08.22 | Guard siren | supplier arrangeing the material
165705 | 17.08.22 | Ms railing | under fabrication work
165710 | 22.08.22 | cp items | Pick up from Ssllp
165712 | 22.08.22 | cp items | Pick up from Ssllp
165714 | 22.08.22 | cp items | Pick up from Ssllp
165719 | 30.08.22 | Eco-Drain items | Next week they will delivery
165721 | 3.9.22 | Stationery items | Pick up from Ssllp
165724 | 9.9.22 | cp items | Pick up from Ssllp