## MPPL
Prepared by: | Mounika
Report Date | 2022-09-17
Site | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178753 | 09.09.22 | Cement Board | Po No -92016
178740 | 29.08.22 | Cement Board | Po No -92017
178757 | 10.09.22 | MS Angle | Po No -92114
List of requisitions Where PO/WO is prepared and items have not received at site
178127 | 29.01.21 | Wall Hung | Bulk Order
178477 | 31.03.22 | Touhened Glass | Pick from SSLLP
178479 | 05.04.22 | Grills | Pick from SSLLP
178547 | 06.05.22 | Wood Dark tiles | Delivered
178558 | 14.07.22 | Wires | Cancelled
178578 | 31.05.22 | Panel Doors | Cancelled
178617 | 24.06.22 | Malasin Tiles | Pick from GMR
178620 | 27.06.22 | Timer & L & T | Cancelled
178641 | 09.07.22 | Back Pack | Cancelled
178666 | 20.07.22 | Spring Wire | Cancelled
178679 | 30.07.22 | Ranger Blue | Pick from GMR
178706 | 09.08.22 | MS Grills | Pick from SSLLP
178708 | 09.08.22 | Kitchen Cabinate | Work Under Process
178721 | 18.08.22 | Modular plates | Delivered
178722 | 19.08.22 | Chimney-Hindware | Pick from Supplier
178727 | 23.08.22 | CC TV Camera | Pick from SSLLP
178728 | 23.08.22 | Modular plates | Pick from SSLLP
178733 | 26.08.22 | Maysian Brown DK | Pick from SSLLP
178734 | 26.08.22 | Urbanwood tiles | Pick from GMR
178735 | 26.08.22 | Toughned Glass | Pick from Supplier
178738 | 29.08.22 | Waste Coupling | Delivered
178739 | 29.08.22 | MS Grills | Pick from SSLLP
178740 | 29.08.22 | Cement Board | Pick from Supplier
178743 | 05.09.22 | Tab Brown Granite | Pick from SOV
178744 | 05.09.22 | Smile Play | Pick from Supplier
178746 | 06.09.22 | Malasin Tiles | Pick from GMR
178755 | 10.09.22 | Black Berry | Pick from GMR
178756 | 10.09.22 | SS Name Plates | Pick from Supplier
178759 | 10.09.22 | Grout | Delivered
178751 | 07.09.22 | Acid | Delivered