## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-09-16
Site |  | GMR
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Missing requisitions
193772 | 2022-09-05 | UPVC Sliding windows | PO 92165
193802 | 2022-09-09 | Tan brown granite | PO 92113
List of requisitions Where PO/WO not prepared 3 working days after requisition:
193692 | 2022-08-19 | Panel doors | PO 91194
193694 | 2022-08-19 | Tan brown granite | PO 92035, 92138
193769 | 2022-09-05 | Fire steel doors | Approved rates to be receive from Anwar procument
193771 | 2022-09-05 | UPVC Sliding windows | PO 92139
193778 | 2022-09-09 | Electrical wires | PO 91934
193790 | 2022-09-09 | Steel glass balcony railing | PO 92137
193795 | 2022-09-09 | UPVC Windows | PO 91852, 91895
193797 | 2022-09-09 | UPVC Windows | PO 91892
193798 | 2022-09-09 | MS Grills | PO 91790
193801 | 2022-09-09 | UPVC Windows | PO 91844,91891
193802 | 2022-09-09 | Electrical wires | PO 92005
193804 | 2022-09-09 | Tiles- grigio serena | PO 92160
193827 | 2022-09-12 | Drill machine | Cancelled, issued another PO
193829 | 2022-09-12 | False ceiling | PO to be issue- missing req
193830 | 2022-09-12 | Tiles. | PO 92055
193831 | 2022-09-13 | Panel doors&beading | PO 92037
193832 | 2022-09-13 | Araldite, roff chemical, bonding agent | PO 92038
193834 | 2022-09-13 | Tiles | PO 92019
193835 | 2022-09-13 | Red oxided primer | PO 92042
193836 | 2022-09-13 | Vitrified nitco tagus | PO 92021
193840 | 2022-09-14 | CPVC Material | PO to be issue- missing req
193839 | 2022-09-14 | Plumbing material | PO 92154
193843 | 2022-09-14 | Plumbing material | PO 92157
193846 | 2022-09-14 | CPVC Material | PO 92153
193846 | 2022-09-14 | CP Extension nipple | PO 92153
List of requisitions Where PO/WO is prepared and items have not received at site
193505 | 2022-07-21 | MS Grills | Part material deliverd balance under production
193563 | 2022-08-02 | Guard alert siren | Next week delivery
193595 | 2022-08-06 | Plumbing material | Pick up from SSLLP
193606 | 2022-08-08 | Hardware material | Pick up from SSLLP
193621 | 2022-08-10 | Panel doors, SS Hinges, door stopper | Doors, door stoper collect from SSLLP, Hinges will be receving on Monday
193639 | 2022-08-12 | Cement fiber board | Work under process
193644 | 2022-08-13 | CP Material | Deliverd
193699 | 2022-08-20 | PVC Material | Pick up from SSLLP
193728 | 2022-08-24 | UPVC Windows | Part material deliverd balance under production
193770 | 2022-09-05 | Hardware material | Deliverd
193773 | 2022-09-06 | MS Grills | Grills are in powder coating will be deliver in 4-5 days
193779 | 2022-09-05 | CPVC Material | Deliverd
193784 | 2022-09-07 | Tan brown granite | Deliverd
193789 | 2022-09-09 | Electrical material | Pick up from SSLLP
193792 | 2022-09-09 | Panel doors, beading | Pick up from SSLLP
193794 | 2022-09-09 | Electrical material | Pick up from SSLLP
193809 | 2022-09-10 | CPVC Material | Wrong written chek.
193817 | 2022-09-10 | Plumbing material | Deliverd
193818 | 2022-09-10 | CPVC Material | Pick up from SSLLP
193820 | 2022-09-10 | Hardware material | Deliverd
193821 | 2022-09-10 | Tan brown granite | Deliverd
193826 | 2022-09-12 | CP Material | Pick up from SSLLP
193828 | 2022-09-12 | Texture-Scaratch plaster | Deliverd