## Vista
Prepared by: | Ramya
Report Date | 2022-09-23
Site | MHPLSOV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
185281 | 23-08-22 | SS Self drilling screws | PO issued po no 91400,92082
185287 | 14-09-22 | Solid blocks | PO issued po no 91964
List of requisitions Where PO/WO is prepared and items have not received at site
185270 | 2022-02-08 | Electrical guard alert siren | delivery by next week
184288 | 14-09-22 | plumbing PVC Material | pick up from SSLLP