## Vista
Prepared by: | Ramya
Report Date | 2022-09-23
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
184610 | 2022-12-09 | PVC HDPE Over head tank | Cancelled
184611 | 2022-12-09 | PVC HDPE Over head tank | Cancelled
184612 | 2022-12-09 | PVC HDPE Over head tank | Cancelled
184628 | 14-09-22 | Eco drain pipe & eco raiser &eco drain chamber | po issued po no-91991,92089
184629 | 15-09-22 | Tandoor stone | 92007
List of requisitions Where PO/WO is prepared and items have not received at site
184404 | 15-07-22 | Ultra Sprinkle HL, DK , malaysian brown DK | Tiles are production by monday will give info
184405 | 15-07-22 | Ultra Sprinkle HL, DK , malaysian brown DK | Tiles are production by monday will give info
184406 | 15-07-22 | Ultra Sprinkle HL, DK , malaysian brown DK | Tiles are production by monday will give info
184410 | 18-07-22 | malaysian brown DK & HL | Tiles are production by monday will give info
184420 | 19-08-22 | printer cable | Cancelled raise a new req
184477 | 2022-04-08 | UPVC Windows | Deliverd
184485 | 2022-08-08 | Ultra Sprinkle HL, DK , malaysian brown DK&HL | Tiles are production by monday will give info
184495 | 20-08-22 | Ultra Sprinkle HL, | Tiles are production by monday will give info
184512 | 17-08-22 | Electrical conducting material | Tiles are production by monday will give info
184519 | 18-07-22 | CP plumbing material | pick up from SSLLP
184522 | 19-08-22 | V. tiles urbanwood dark | pick up from GMR
184536 | 23-08-22 | Steel MS L patti | Deliverd
184537 | 23-08-22 | PVC door bend 75mmx45*PVC Rigid pipe | pick up from SSLLP
184545 | 24-08-22 | Electrical copper wire | Deliverd
184552 | 29-08-22 | Anchor bolt pin type | delivery by monday
184560 | 29-08-22 | Tile adhesive roff & CC Bonding agent | pick up from SSLLP
184563 | 30-08-22 | panel doors | delivery by Wenesday
184564 | 2022-01-09 | UPVC Windows | delivery by Wenesday
184565 | 2022-01-09 | CPVC FTA Adapter brass 15 no pending | Deliverd
184566 | 2022-02-09 | Electrical copper wire | delivery by Wenesday
184567 | 2022-02-09 | Hardware plywood | delivery by Wenesday
184568 | 2022-02-09 | panel doors | delivery by Wenesday
184569 | 2022-02-09 | panel doors | delivery by Wenesday
184570 | 2022-03-09 | UPVC Windows | fallow up with supplier
184571 | 2022-03-09 | panel doors | delivery by Wenesday
184572 | 2022-03-09 | Electrical copper wire | pick up from SSLLP
184573 | 2022-05-09 | Ispira crema marfil tiles | Deliverd
184574 | 2022-05-09 | wall & floor tile | Tiles are production by monday will give info
184575 | 2022-05-09 | wall & floor tile | Tiles are production by monday will give info
184577 | 2022-05-09 | wall & floor tile | Tiles are production by monday will give info
184578 | 2022-06-09 | UPVC Windows | fallow up with supplier
184579 | 2022-08-09 | Electrical copper wire | pick up from SSLLP
184580 | 2022-08-09 | Electrical copper wire | pick up from SSLLP
184583 | 2022-08-09 | Electrical round covers PVC | pick up from SSLLP
184598 | 2022-10-09 | Electrical conducting material | pick up from SSLLP
184602 | 2022-10-09 | Conceled flush tanks | Deliverd
184603 | 2022-10-09 | Conceled flush tanks | Deliverd
184604 | 2022-10-09 | Conceled flush tanks | pick up from SSLLP
184605 | 2022-10-09 | Electrical conducting material | pick up from SSLLP
184606 | 2022-10-09 | electrical fan box pvc 25mm | pick up from SSLLP
184608 | 2022-12-09 | wall & floor tile | Tiles are production by monday will give info
184609 | 2022-12-09 | wall & floor tile | Tiles are production by monday will give info
184610 | 2022-12-09 | CPVC material | Deliverd
184611 | 2022-12-09 | CPVC material | pick up from SSLLP
184612 | 2022-12-09 | CPVC material | Deliverd
184613 | 2022-12-09 | CPVC Pipe20mm & cpvc end cap | Deliverd
184614 | 2022-12-09 | Tile adhesive roff & CC Bonding agent | pick up from SSLLP
184617 | 2022-12-09 | tiles ispira urban wood dark | Tiles are production by monday will give info
184618 | 2022-12-09 | cpvc reducer MTA & FTA CP Angle cock | Deliverd
184627 | 14-09-22 | Electrical switches | Deliverd