## NE
Prepared by: | Ramya
Report Date | 17.09.22
Site | Serene Farms
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
150646 | 15-07-22 | Electrical meterials | delivery by monday
150644 | 2022-09-07 | Plumbing material | delivery by monday
150648 | 2022-04-08 | Plumbing material | delivery by monday
150649 | 2022-04-08 | Plumbing material | delivery by monday
150650 | 2022-04-08 | Plumbing material | delivery by monday
150651 | 2022-04-08 | Electrical meterials | delivery by monday