## NE
Prepared by: | Ramya
Report Date | 24.10.22
Site | Nilgiri Estates
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
175513 | 23-06-2022 | ward robe | material already deliverd
List of requisitions Where PO/WO is prepared and items have not received at site
175325 | 20-07-2021 | solar module | Legal case is going on supplier
175492 | 2022-07-03 | Sliding windows | fallow up with supplier
175517 | 15-07-2022 | Floor tiles | pick up from GMR
175524 | 19-08-22 | CP material | fallow up with supplier
175525 | 19-08-22 | MS Grills | pick up from ssllp
175526 | 2022-08-09 | cleaning material | pick up from ssllp
175528 | 14.09.22 | Tables | deliver