## Vista
Prepared by: | vanajakshi
Report Date | 29.09.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142152 | 18.08.2022 | Toys & dolls | Po to be issue
142188 | 07.09.2022 | Gas cylinder | Local Purchase
142206 | 19.09.2022 | Plumbing PVC | PO:92362
List of requisitions Where PO/WO is prepared and items have not received at site
142037 | 04.07.2022 | Floor large tiles | Awaiting for Arranging material
142040 | 04.07.2022 | Malasian brown DK | Awaiting for Arranging material
142051 | 07.07.2022 | Large tiles(Tagus & marbo opera)tiles | Awaiting for Arranging material
142052 | 7.07.2022 | Regal beige & urbanwood dark tiles | Awaiting for Arranging material
142054 | 07.07.2022 | Large tiles | Awaiting for Arranging material
142070 | 14.07.2022 | Malasian brown DK &HL | Awaiting for Arranging material
142087 | 20.07.2022 | Taugs | Awaiting for Arranging material
142102 | 26.07.2022 | Armoured cable | Delivered
142112 | 1.08.2022 | Powder caoted grill | Awaiting for Arranging material
142115 | 02.08.2022 | Guard alert siren | Awaiting for Arranging material
142125 | 04.08.2022 | Ceramic wall tiles | Awaiting for Arranging material
142137 | 9.08.2022 | cable tray | Supplier arranging material
142139 | 11.08.2022 | cpvc material | Pick up from SSLLP
142171 | 2.09.2022 | Panel door & door stopper | Delivered
142184 | 6.09.2022 | Paints | Delivered
142189 | 07.09.2022 | Traventine corolina & urbanwood light | Delivered
142199 | 16.09.2022 | GI Universal clamp | Supplier arranging material
142205 | 19.09.2022 | Electrical copper wire | Pick up from SSLLP