## Vista
Prepared by: | Ramya
Report Date | 2022-10-01
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
184485 | 2022-08-08 | Ultra Sprinkle HL, DK , malaysian brown DK | pick up from GMR
184495 | 20-08-22 | Ultra Sprinkle HL, | pick up from GMR
184522 | 19-08-22 | V. tiles urbanwood dark | pick up from GMR
184536 | 23-08-22 | Steel MS L patti | Deliverd
184537 | 23-08-22 | PVC door bend 75mmx45*PVC Rigid pipe | pick up from SSLLP
184560 | 29-08-22 | Tile adhesive roff & CC Bonding agent | pick up from SSLLP
184564 | 2022-01-09 | UPVC Windows | follow up with supplier
184565 | 2022-01-09 | CPVC FTA Adapter brass 15 no pending | pick up from SSLLP
184567 | 2022-02-09 | Hardware plywood | Deliverd
184568 | 2022-02-09 | panel doors | Deliverd
184569 | 2022-02-09 | panel doors | Deliverd
184570 | 2022-03-09 | UPVC Windows | fallow up with supplier
184571 | 2022-03-09 | panel doors | Deliverd
184574 | 2022-05-09 | wall & floor tile | pick up from GMR
184575 | 2022-05-09 | wall & floor tile | pick up from GMR
184577 | 2022-05-09 | wall & floor tile | pick up from GMR
184578 | 2022-06-09 | UPVC Windows | fallow up with supplier
184580 | 2022-08-09 | Electrical copper wire | pick up from SSLLP
184583 | 2022-08-09 | electrical round covers | pick up from SSLLP
184598 | 2022-10-09 | electrical fan box | pick up from SSLLP
184605 | 2022-10-09 | electrical fan box | pick up from SSLLP
184606 | 2022-10-09 | electrical fan box | pick up from SSLLP
184608 | 2022-12-09 | wall & floor tile | pick up from GMR
184609 | 2022-12-09 | wall & floor tile | pick up from GMR
184611 | 2022-12-09 | CPVC Material | pick up from SSLLP
184617 | 2022-12-09 | Tiles ispira urbanwood dark | pick up from GMR
184629 | 15-09-22 | tandoor polished stone | fallow up with supplier
184630 | 16-09-22 | General items | Deliverd
184632 | 16-09-22 | RCC Spacers all in one | Deliverd
184641 | 19-09-22 | wall & floor tile | pick up from GMR
184642 | 19-09-22 | wall & floor tile | pick up from GMR
184643 | 20-09-22 | Electrical switches & MCB | pick up from SSLLP
184644 | 20-09-22 | Electrical switches & MCB | pick up from SSLLP