## Vista
Prepared by: | vanajakshi
Report Date | 28.09.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142071 | 14.07.2022 | Channel Bracket | Cancelled Requisition .If u want this material please raise the new requisition.
142102 | 26.07.2022 | Armoured cable | PO NO:90612.
142117 | 2.08.2022 | GI round nut | PO to be issue
142137 | 9.08.2022 | Cable tray | PO:91169
142152 | 18.08.2022 | Toys & dolls | Po to be issue
142188 | 07.09.2022 | Gas cylinder | Local Purchase
List of requisitions Where PO/WO is prepared and items have not received at site
141964 | 11.06.2022 | Floor tile country almond | Awaiting for Arranging material
142003 | 24.06.2022 | Bathroom wall tiles | Awaiting for Arranging material
142028 | 1.07.2022 | Mopping stick holder | Delivered
142037 | 04.07.2022 | Floor large tiles | Awaiting for Arranging material
142040 | 04.07.2022 | Malasian brown DK | Awaiting for Arranging material
142051 | 07.07.2022 | Large tiles(Tagus & marbo opera)tiles | Awaiting for Arranging material
142052 | 7.07.2022 | Regal beige & urbanwood dark tiles | Awaiting for Arranging material
142054 | 07.07.2022 | Large tiles | Awaiting for Arranging material
142160 | 24.08.2022 | SS Name plate | Delivered
142075 | 15.07.2022 | Creche toys &books | Next week delivery
142087 | 20.07.2022 | Taugs | Awaiting for Arranging material
142112 | 1.08.2022 | Powder caoted grill | Awaiting for Arranging material
142115 | 02.08.2022 | Guard alert siren | Awaiting for Arranging material
142125 | 04.08.2022 | Ceramic wall tiles | Awaiting for Arranging material
142139 | 11.08.2022 | CPVC Material | Pick Up From SSLLP
142060 | 11.07.2022 | CP Short body | Pick Up From SSLLP
142171 | 2.09.2022 | Panel door & door stopper | Delivered
142181 | 6.09.2022 | CPVC Elbow | Delivered
142183 | 6.09.2022 | Reducer Tee | Delivered
142184 | 6.09.2022 | Paints | Delivered
142186 | 07.09.2022 | LED square surface light | Delivered
142189 | 07.09.2022 | Traventine corolina & urbanwood light | Delivered