## MPPL
Prepared by: | Mounika
Report Date | 2022-09-24
Site | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
178127 | 29.01.21 | Wall Hung | Bulk Order
178477 | 31.03.22 | Touhened Glass | Pick from SSLLP
178479 | 05.04.22 | Grills | Pick from SSLLP
178617 | 24.06.22 | Malasin Tiles | Pick from GMR
178679 | 30.07.22 | Ranger Blue | Pick from GMR
178706 | 09.08.22 | MS Grills | Pick from SSLLP
178708 | 09.08.22 | Kitchen Cabinate | Work Completed
178722 | 19.08.22 | Chimney-Hindware | Pick from Supplier
178727 | 23.08.22 | CC TV Camera | Pick from SSLLP
178728 | 23.08.22 | Modular plates | Pick from SSLLP
178733 | 26.08.22 | Maysian Brown DK | Pick from SSLLP
178734 | 26.08.22 | Urbanwood tiles | Pick from GMR
178735 | 26.08.22 | Toughned Glass | Pick from Supplier
178737 | 29.08.22 | CP Nipple | Delivered
178739 | 29.08.22 | MS Grills | Pick from SSLLP
178740 | 29.08.22 | Cement Board | Pick from Supplier
178743 | 05.09.22 | Tab Brown Granite | Pick from SOV
178746 | 06.09.22 | Malasin Tiles | Pick from GMR
178755 | 10.09.22 | Black Berry | Pick from GMR
178757 | 10.09.22 | MS Angle | Delivered
178760 | 14.09.22 | Flush Plates | Pick from Supplier
178761 | 19.09.22 | Acid | Delivered
178762 | 19.09.22 | Roofing sheet | Pick from Supplier
178763 | 19.09.22 | Anchor Bolt | Pick from SSLLP
178764 | 20.09.22 | MS Grills | Pick from SSLLP
178766 | 20.09.22 | Copper wire | Pick from SSLLP
178767 | 22.09.22 | Tandoor stone | Pick from Supplier
178768 | 22.09.22 | Ceiling Down Lights | Pick from Supplier