## Vista
Prepared by: | Ramya
Report Date | 2022-10-08
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
184485 | 2022-08-08 | Ultra Sprinkle HL, DK , malaysian brown DK | pick up from GMR
184495 | 20-08-22 | Ultra Sprinkle HL, | pick up from GMR
184522 | 19-08-22 | V. tiles urbanwood dark | pick up from GMR
184564 | 23-08-22 | UPVC Windows | fallow up with supplier
184570 | 23-08-22 | UPVC Windows | fallow up with supplier
184571 | 29-08-22 | Cylinderical lock & ss hinges & magnetic door stopper | pick up from SSLLP
184574 | 2022-01-09 | wall & floor tile | pick up from GMR
184575 | 2022-01-09 | wall & floor tile | pick up from GMR
184577 | 2022-02-09 | wall & floor tile | pick up from GMR
184578 | 2022-02-09 | UPVC Windows | fallow up with supplier
184580 | 2022-02-09 | Electrical copper wire | pick up from SSLLP
184608 | 2022-03-09 | wall & floor tile | fallow up with supplier
184609 | 2022-03-09 | wall & floor tile | fallow up with supplier
184617 | 2022-05-09 | Tiles ispira urbanwood dark | pick up from GMR
184630 | 2022-05-09 | General items | Deliverd
184632 | 2022-05-09 | RCC Spacers all in one | fallow up with supplier
184641 | 2022-06-09 | Crema marfil & urbanwood natural country rosso | pick up from GMR
184642 | 2022-08-09 | wall & floor tile malasian brown & luna & jaipur panna | pick up from GMR
184643 | 2022-08-09 | MCB 6 AMPS | pick up from SSLLP
184645 | 2022-10-09 | Electrical copper wire | pick up from SSLLP
184646 | 2022-10-09 | Electrical copper wire | pick up from SSLLP
184652 | 2022-10-09 | elecrical switches | pick up from SSLLP
184657 | 2022-12-09 | Electrical copper wire | pick up from SSLLP
184658 | 2022-12-09 | electrical isolator | pick up from SSLLP
184661 | 2022-12-09 | CPVC FTA & HDPE pipe | pick up from SSLLP
184662 | 2022-12-09 | Cleaning material | Deliverd
184664 | 15-09-22 | Eco drain material | fallow up with supplier
184665 | 16-09-22 | internal door beading | Deliverd