## Vista
Prepared by: | Venkateshwarlu
Report Date | 2022-10-08
Site | MHPLSOV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
185270 | 2022-02-08 | Guard alert siren | delivery by next week
184281 | 23-08-22 | SS Self drilling screws | Deliverd
185297 | 21-09-22 | Electrical DB TPN & MCB &Fiber box | Deliverd
185295 | 20-09-22 | FRP Manhole cover | Deliverd On Tueseday
185304 | 27.09.22 | Alu.Armd Cable 4Cx6Sqrmm & 2Cx4Sqrmm 4mm Al.Service Wire | 4mm Service Wire Delivered,Alu.Armd Cables Delivery By Next Week
185305 | 27.09.22 | Curb Stone | Deliverd