## Sheet1
Prepared by: | Venkateshwarlu.P
Report Date | 2022-10-08
Site | NE
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
175325 | 20.07.2021 | Solar Module | Cancelled by Site
175492 | 07.03.2022 | Sliding Windows | Cancelled by Site
175517 | 15.07.2022 | Floor Tiles | Cancelled by Site
175525 | 19.08.2022 | MS Grill | Ready For Lifting at SOV
175526 | 08.09.2022 | Cleaning Material | Delivered by Monday
175531 | 23.09.2022 | Blinds | Delivered by Monday
175533 | 27.09.22 | Chairs | Delivered