## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-10-01
Site |  | GMR
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Missing requisitions
193920 | 2022-09-17 | GI Thread rod | PO to be issue- missing req
List of requisitions Where PO/WO not prepared 3 working days after requisition:
193927 | 2022-09-27 | PVC Material | PO to be issue
193769 | 2022-09-05 | Fire steel door single shutter | Quotes to be receive
193772 | 2022-09-05 | UPVC Windows | Comparision statement sent to md for approval
193795 | 2022-09-09 | UPVC Windows | Comparision statement sent to md for approval
193797 | 2022-09-09 | UPVC Windows | Comparision statement sent to md for approval
193800 | 2022-09-12 | UPVC Windows | Comparision statement sent to md for approval
193801 | 2022-09-09 | UPVC Windows | Comparision statement sent to md for approval
193902 | 2022-09-24 | MS Round pipe B class | PO to be issue
193908 | 2022-09-24 | PVC Material | PO to be issue
193910 | 2022-09-24 | CPVC Material | PO to be issue
193913 | 2022-09-24 | Panel doors & beading | PO 92328
193930 | 2022-09-27 | Hardware material | PO 92511, 92514
193935 | 2022-09-27 | Hardware material | PO 92510, 92515
193936 | 2022-09-27 | MS L angle, MS Round pipe hardware material | PO 92621, 92622
193939 | 2022-09-27 | CPVC Material | PO 92570
List of requisitions Where PO/WO is prepared and items have not received at site
193595 | 2022-08-06 | Plumbing material | Pick up from SSLLP
193606 | 2022-08-08 | Hardware material | Pick up from supplier SFS
193607 | 2022-08-08 | Electrical material | Pick up from SSLLP
193613 | 2022-08-09 | Vermicompost | Deliverd
193692 | 2022-08-19 | Panel doors and beading | Pick up from SSLLP
193788 | 2022-09-09 | 118 Yellow wire and black wire | Deliverd
193802 | 2022-09-09 | Electrical material | Deliverd
193814 | 2022-09-10 | Hammer drill machine | Deliverd
193820 | 2022-09-10 | Hammer drill machine | Deliverd
193834 | 2022-09-13 | Tagus tiles | Pick up from SSLLP
193840 | 2022-09-14 | CPVC FAPT | Pick up from SSLLP
193852 | 2022-09-15 | MS Square pipe | Pick up from Supplier Arihant
193885 | 2022-09-21 | Electrical material | Pick up from SSLLP
193895 | 2022-09-22 | CPVC Material | Deliverd
193903 | 2022-09-24 | Electrical material | Pick up from SSLLP
193904 | 2022-09-24 | Electrical material | Pick up from SSLLP
193907 | 2022-09-24 | PVC Material | Pick up from SSLLP
193923 | 2022-09-27 | Tile grout cement white | Deliverd
193926 | 2022-09-27 | PVC Material | Pick up from SSLLP
193938 | 2022-08-27 | Electrical material | Pick up from SSLLP
193943 | 2022-09-27 | CPVC Material | Pick up from SSLLP
193944 | 2022-09-27 | CPVC Material | Pick up from SSLLP