## Vista
Prepared by: | vanajakshi
Report Date | 08.10.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142211 | 22.09.2022 | Plumbing material | PO NO:92285
142188 | 07.09.2022 | Gas cylinder | Local Purchase
142218 | 28.09.2022 | MS grills | PO NO:92445
List of requisitions Where PO/WO is prepared and items have not received at site
142037 | 04.07.2022 | Floor large tiles | Awaiting for Arranging material
142040 | 04.07.2022 | Malasian brown DK | Awaiting for Arranging material
142051 | 07.07.2022 | Large tiles(Tagus & marbo opera)tiles | Delivered
142052 | 7.07.2022 | Regal beige & urbanwood dark tiles | Delivered
142070 | 14.07.2022 | Malasian brown DK &HL | Awaiting for Arranging material
142075 | 15.07.2022 | Building block | Next week Delivery
142087 | 20.07.2022 | Taugs | Collect from SSLLP
142112 | 1.08.2022 | Powder caoted grill | Awaiting for Arranging material
142115 | 02.08.2022 | Guard alert siren | Supplier arranging material
142137 | 9.08.2022 | cable tray | Supplier arranging material
142139 | 11.08.2022 | cpvc material | Pick up from SSLLP
142208 | 21.09.2022 | Plumbing material | Supplier arranging material
142208 | 21.09.2022 | Submersible pump | Delivered