## KNM
Prepared by: | sneha
Report Date | 8.10.22
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
165738 | 27.9.22 | Al.Windows | Estimate to be prepared
165739 | 27.09.22 | Al.Windows | Estimate to be prepared
List of requisitions Where PO/WO is prepared and items have not received at site
07.5.22
165664 | 26.5.22 | Garbage Bin | Next week they will delivery
165688 | 06.07.22 | MS Grill | Pick up from Ssllp
165701 | 2.8.22 | Guard siren | Next week they will delivery
165705 | 17.8.22 | Ms railing | powder coating under process
165726 | 9.9.22 | Extension nipple | Pick up from Ssllp
165729 | 13.09.22 | plywood for display | delivered
165732 | 17.09.22 | grass&plants | Next week they will delivery
165734 | 20.09.22 | CPVC PIPE | pick up from ssllp
1657335 | 20.09.22 | Eco chamber cover | Pick up from Ssllp
165736 | 26.09.22 | External paint | Pick up from Ssllp
165737 | 27.09.22 | panel Door | Pick up from Ssllp
165740 | 27.09.22 | MS Grill | under fabrication work
165741 | 27.09.22 | MS Grill | under fabrication work
165742 | 27.09.22 | SS Scrws | Pick up from Ssllp
165743 | 27.09.22 | Sanitary items | Pick up from Ssllp
165744 | 27.09.22 | CP items. | Pick up from Ssllp