## KNM
Prepared by: | sneha
Report Date | 23.9.22
Site | AGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
07.5.22
165664 | 26.5.22 | Garbage Bin | Next week they will delivery
165688 | 06.07.22 | MS Grill | Powder coated not done
165701 | 2.8.22 | Guard siren | Next week they will delivery
165705 | 17.8.22 | Ms railing | under fabrication work
165710 | 22.08.22 | cp items | Pick up from Ssllp
165712 | 22.08.22 | cp items | Pick up from Ssllp
165714 | 22.8.22 | cp items | material recieved
165721 | 3.9.22 | Stationery items | pick up from ssllp
165724 | 09.09.22 | cp items | Pick up from Ssllp
165726 | 09.09.22 | cp items | Pick up from Ssllp
165729 | 13.09.22 | plywood for display | Next week they will delivery
165731 | 17.09.22 | tandoor stone | Next week they will delivery
165732 | 17.09.22 | grass&plants | Next week they will delivery