## KNM
Prepared by: | Kavitha
Report Date | 2022-10-09
Site | DR.NRK Biotech Pvt Ltd
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186415 | 28-09-22 | Proportion box | Po to be issue
186418 | 2022-01-10 | Binding wire | Esimate with MD Sir
List of requisitions Where PO/WO is prepared and items have not received at site
186375 | 2022-03-08 | Guard alert- siren | Follow up with supplier
186405 | 20-09-22 | Pin vibrator | Pick up from supplier