## Vista
Prepared by: | Ramya
Report Date | 2022-25-08
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
184421 | 20-07-22 | Headset-JBL | delivery by tomorrow
184483 | 2022-06-08 | GI wire pvc coated | deliverd
184507 | 17-08-22 | Plumbing CP material | Po issued-Po no-91215
184509 | 17-08-22 | Electrical conducting material | Po issued-Po no-91231
184510 | 17-08-22 | Electrical conducting material | Po issued-Po no-91232
184511 | 17-08-22 | Electrical conducting material | Po issued-Po no-91321
184512 | 17-08-22 | Electrical conducting material | Po issued-Po no-91229
184513 | 17-08-22 | Electrical conducting material | Po issued-Po no-91227
184514 | 17-08-22 | Electrical conducting material | Po issued-Po no-91228
184515 | 17-08-22 | Electrical conducting material | Po issued-Po no-91213
List of requisitions Where PO/WO is prepared and items have not received at site
184324 | 30-06-22 | gate lights | deliverd
184368 | 2022-02-07 | pad locks | deliverd
184372 | 28-07-22 | ultra sprinkle HL luna DK & HL | pick up from GMR
184404 | 15-07-22 | Wall & floor tiles | pick up from GMR
184405 | 15-07-22 | Wall & floor tiles | pick up from GMR
184406 | 15-07-22 | Wall & floor tiles | pick up from GMR
184410 | 18-07-22 | Wall & floor tiles | pick up from GMR
184420 | 19-07-22 | printer cable | delivery by next week
184461 | 29-07-22 | wall hung EWC with seat cover | pick up from SSLLP
184463 | 2022-01-08 | crack fill chemical | follow up with supplier
184468 | 2022-03-08 | panel main doors | pick up from SSLLP
184474 | 2022-03-08 | wall plug fisher | pick up from SSLLP
184480 | 2022-05-08 | plumbing sanitary | pick up from SSLLP
184484 | 2022-08-08 | vertified nitco biblios | deliverd
184485 | 2022-08-08 | nitco wall & floor tiles | deliverd
184502 | 16-08-22 | cpvc material | deliverd