## NE
Prepared by: | Ramya
Report Date | 19.08.22
Site | Seren construction LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
150646 | 15-07-22 | Electrical materials | pick up from SSLLP
150644 | 09-0722 | Plumbing material | follow up with supplier
150648 | 2022-04-08 | Plumbing material | pick up from SSLLP
150649 | 2022-04-08 | Plumbing material | pick up from SSLLP
150650 | 2022-04-08 | Plumbing material | pick up from SSLLP
150651 | 2022-04-08 | Electrical materials | pick up from SSLLP