## KNM
Prepared by: | Deepa
Report Date | 14.10.22
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
95181 | 02.08.22 | Security Guard alert siren | Next weak Delivery
95197 | 03.09.22 | Electrical conducting | Pick up from SSLLP
95211 | 22.09.22 | pvc plumbing material | Pick up from SSLLP
95212 | 22.09.22 | Cpvc brass tee | Pick up from SSLLP
95214 | 30.09.22 | General material | Pick up from SSLLP