## Vista
Prepared by: | vanajakshi
Report Date | 14.10.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142188 | 07.09.2022 | Gas cylinder | Local Purchase
142223 | 29.09.2022 | PVC false ceiling | po:92529
142227 | 1.10.2022 | MS round pipe | po:92663
142230 | 1.10.2022 | MS L angle flat patti | po:92656,62654
142231 | 3.10.2022 | Plumbing cpvc | po:92661
142232 | 3.10.2022 | Electrical material | po:92686
142235 | 4.10.2022 | UPVC Windows | Estimation sent to MD'S Approoval
142236 | 4.10.2022 | Doors & hardware | po:92696
142238 | 4.10.2022 | Glass railing | po:92682
List of requisitions Where PO/WO is prepared and items have not received at site
142037 | 04.07.2022 | Floor large tiles | Awaiting for Arranging material
142040 | 04.07.2022 | Malasian brown DK | Awaiting for Arranging material
142051 | 07.07.2022 | Large tiles(Tagus & marbo opera)tiles | Awaiting for Arranging material
142052 | 7.07.2022 | Regal beige & urbanwood dark tiles | Awaiting for Arranging material
142070 | 14.07.2022 | Malasian brown DK & HL | Awaiting for Arranging material
142075 | 15.07.2022 | Building block | Next week delivery
142087 | 20.07.2022 | Taugs | Delivered
142112 | 1.08.2022 | Powder coated grills | Awaiting for Arranging material
142115 | 2.08.2022 | Guard alert siren | Supplier Arranging Material
142121 | 3.08.2022 | Vertified tiles | Awaiting for Arranging material
142125 | 4.08.2022 | Ceramic wall tiles | Awaiting for Arranging material
142137 | 9.08.2022 | Cable tray | Delivered
142139 | 11.08.2022 | CPVC material | Next week delivery
142215 | 26.09.2022 | Plumbing cpvc | Next week delivery
142216 | 24.09.2022 | Kajariya dyna tiles | Next week delivery
142229 | 1.10.2022 | Plumbing rigid elbow | Awaiting for Arranging material
Next week delivery