## MPPL
Prepared by: | Mounika
Report Date | 08.10.22
Site | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178783 | 04.10.22 | Boom Barrier | Quote to be receive
178784 | 04.10.22 | Traffic Cone | Quote to be receive
List of requisitions Where PO/WO is prepared and items have not received at site
178127 | 29.01.21 | Wall Hung | Bulk Order
178477 | 31.03.22 | Touhened Glass | Pick from SSLLP
178479 | 05.04.22 | Grills | Pick from SSLLP
178617 | 24.06.22 | Malasin Tiles | Pick from GMR
178679 | 30.07.22 | Ranger Blue | Pick from GMR
178689 | 02.08.22 | Guard alert | Pick from Supplier
178706 | 09.08.22 | MS Grills | Pick from SSLLP
178722 | 19.08.22 | Chimney-Hindware | Pick from Supplier
178728 | 23.08.22 | Modular plates | Pick from SSLLP
178733 | 26.08.22 | Maysian Brown DK | Pick from SSLLP
178734 | 26.08.22 | Urbanwood tiles | Pick from GMR
178735 | 26.08.22 | Toughned Glass | Pick from Supplier
178739 | 29.08.22 | MS Grills | Pick from SSLLP
178740 | 29.08.22 | Cement Board | Work under process
178743 | 05.09.22 | Tab Brown Granite | Pick from SOV
178744 | 05.09.22 | Smile play | Pick from Supplier
178746 | 06.09.22 | Malasin Tiles | Pick from GMR
178755 | 10.09.22 | Black Berry | Pick from GMR
178762 | 19.09.22 | Roofing sheet | Pick from Supplier
178763 | 19.09.22 | Anchor Bolt | Pick from SSLLP
178764 | 20.09.22 | MS Grills | Pick from SSLLP
178766 | 20.09.22 | Copper wire | Pick from SSLLP
178770 | 26.09.22 | CP Wall Mixture | Pick from SSLLP
178771 | 26.09.22 | Waste Coupling | Pick from SSLLP
178778 | 30.09.22 | Panel Doors | Pick from SSLLP
178779 | 04.10.22 | False Ceiling | Pick from SSLLP
178780 | 01.10.22 | Stationary | Pick from SSLLP
178781 | 01.10.22 | Insulation | Pick from SSLLP