## Vista
Prepared by: | Ramya
Report Date | 2022-10-14
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
184682 | 2022-03-10 | Macharla stone Red & yellow chocolate | Estimate sent ti MDs approval
List of requisitions Where PO/WO is prepared and items have not received at site
184564 | 2022-01-09 | UPVC Windows | Work completed
184870 | 2022-03-09 | UPVC Windows | Work completed
184871 | 2022-03-09 | Cylinderical lock & ss hinges & magnetic door stopper | Deliverd
184874 | 2022-05-09 | wall & floor tile malasian brown & luna & jaipur panna | pick up from GMR
184575 | 2022-05-09 | wall & floor tile | pick up from GMR
184577 | 2022-05-09 | wall & floor tile malasian brown & luna & jaipur panna | pick up from GMR
184578 | 2022-06-09 | UPVC Windows | Work completed
184580 | 2022-08-09 | Electrical copper wire | pick up from SSLLP
184608 | 2022-12-09 | wall & floor tile ultra sprinkle & malasian brown DK & LT | pick up from GMR
184617 | 2022-12-09 | Tiles ispira urbanwood dark | pick up from GMR
184642 | 19-09-22 | wall & floor tile malasian brown & luna & jaipur panna | pick up from GMR
184645 | 23-09-22 | Electrical copper wire | pick up from SSLLP
184646 | 23-09-22 | Electrical copper wire | pick up from SSLLP
184657 | 23-09-22 | Electrical copper wire | pick up from SSLLP
184658 | 26-09-22 | elecrical switches | pick up from SSLLP
184661 | 26-09-22 | CPVC FTA & HDPE pipe | fallow up with supplier
184664 | 27-09-22 | Eco drain material | Deliverd
184666 | 2022-07-10 | Furniture & fixture HOB | fallow up with supplier
184667 | 28-09-22 | Electrical copper wire | pick up from SSLLP
184668 | 28-09-22 | Furniture & fixture HOB | fallow up with supplier
184669 | 28-09-22 | Furniture & fixture HOB | fallow up with supplier
184670 | 28-09-22 | Furniture & fixture HOB | fallow up with supplier
184675 | 30-09-22 | Gunny bags & sponges | pick up from SSLLP
184679 | 2022-03-10 | Electrical copper wire | pick up from SSLLP
184680 | 2022-03-10 | CP Shower arm & shower head & health faucet & angle | pick up from SSLLP
184681 | 2022-03-10 | CP Sanitary wash basin | Deliverd
184683 | 2022-04-10 | CPVC Material | pick up from SSLLP
184684 | 2022-04-10 | CPVC Material | pick up from SSLLP
184685 | 2022-04-10 | CPVC Material | pick up from SSLLP