## Vista
Prepared by: | vanajakshi
Report Date | 21.10.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142188 | 07.09.2022 | Gas cylinder | Local Purchase
142235 | 4.10.2022 | UPVC material | po to be issue
142267 | 11.10.2022 | HDPE pipe | PO:92865
List of requisitions Where PO/WO is prepared and items have not received at site
142037 | 04.07.2022 | Floor large tiles | Part Material delivered .If you want the remaining material raise new req.
142040 | 04.07.2022 | Malasian brown DK | Part Material delivered .If you want the remaining material raise new req.
142052 | 7.07.2022 | Regal beige & urbanwood dark tiles | Part Material delivered .If you want the remaining material raise new req.
142070 | 14.07.2022 | Malasian brown DK & HL | Part Material delivered .If you want the remaining material raise new req.
142075 | 15.07.2022 | Building block | Next week delivery
142087 | 20.07.2022 | Taugs | Delivered
142115 | 2.08.2022 | Guard alert siren | Supplier Arranging Material
142121 | 3.08.2022 | Vertified tiles | Part Material delivered .If you want the remaining material raise new req.
142125 | 4.08.2022 | Ceramic wall tiles | Delivered
142216 | 24.09.2022 | Kajariya dyna tiles | Delivered
142218 | 28.09.2022 | Steel MS grills | Awaiting for arranging the material
142226 | 30.09.2022 | Concealed tank | partially delivered
142231 | 3.10.2022 | CPVC material | partially delivered
142236 | 4.10.2022 | Doors & Hardware | partially delivered
142238 | 4.10.2022 | Glass balcony railing | Supplier Arranging Material
142243 | 6.10.2022 | CP sanitary | partially delivered
142245 | 6.10.2022