## Vista
Prepared by: | Ramya
Report Date | 21-10-22
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
184574 | 2022-05-09 | wall & floor tile malasian brown & luna & jaipur panna | pick up from GMR
184575 | 2022-05-09 | wall & floor tile ultra sprinkle & malasian brown DK & LT | pick up from GMR
184577 | 2022-05-09 | wall & floor tile ultra sprinkle & malasian brown DK & LT | pick up from GMR
184580 | 2022-08-09 | Electrical copper wire | pick up from SSLLP
184608 | 2022-12-09 | wall & floor tile malasian brown & jaipur panna | pick up from GMR
184617 | 2022-12-09 | Tiles ispira urbanwood dark | pick up from GMR
184642 | 19-09-22 | wall & floor tile malasian brown & jaipur panna | pick up from GMR
184645 | 23-09-22 | Electrical copper wire | pick up from SSLLP
184646 | 23-09-22 | Electrical copper wire | pick up from SSLLP
184657 | 23-09-22 | Electrical copper wire | pick up from SSLLP
184658 | 26-09-22 | elecrical switches | pick up from SSLLP
184661 | 26-09-22 | CPVC FTA & HDPE pipe | pick up from SSLLP
184666 | 2022-07-10 | Furniture & fixture HOB | fallow up with supplier
184667 | 28-09-22 | Electrical copper wire | pick up from SSLLP
184668 | 28-09-22 | Furniture & fixture HOB | fallow up with supplier
184669 | 28-09-22 | Furniture & fixture HOB | fallow up with supplier
184670 | 28-09-22 | Furniture & fixture HOB | fallow up with supplier
184675 | 30-09-22 | Gunny bags & sponges | pick up from SSLLP
184679 | 2022-03-10 | Electrical copper wire | pick up from SSLLP
184680 | 2022-03-10 | CP Shower arm & shower head & health faucet & angle | pick up from SSLLP
184682 | 2022-03-10 | Macharla stone red & yellow chocolate colour | fallow up with supplier
184685 | 2022-04-10 | CPVC Material | pick up from SSLLP
184689 | 2022-08-10 | PVC Single socket pipe | pick up from SSLLP
184690 | 2022-10-10 | Plumbing CP material | pick up from SSLLP
184691 | 2022-10-10 | CP Sanitary material | pick up from SSLLP
184692 | 2022-10-10 | Plumbing CP material | pick up from SSLLP
184693 | 2022-10-10 | CP Sanitary material | pick up from SSLLP
184694 | 2022-10-10 | UPVC Windows | fallow up with supplier
184697 | 2022-12-10 | General items | pick up from SSLLP
184698 | 2022-12-10 | Electrical copper wire | pick up from SSLLP
184669 | 2022-12-10 | Electrical copper wire | pick up from SSLLP
184700 | 2022-12-10 | Electrical copper wire | pick up from SSLLP