## MPPL
Prepared by: | Mounika
Report Date | 22.10.22
Site | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178783 | 04.10.22 | Boom Barrier | Quote to be receive
178891 | 13.10.22 | RO Plant | Quote to be receive
178796 | 17.10.22 | Acid | Po No 93197
178797 | 17.10.22 | Sponges | Po No93195
178803 | 21.10.22 | Coffee Powder | Po No-93162
List of requisitions Where PO/WO is prepared and items have not received at site
178477 | 31.03.22 | Touhened Glass | Pick from SSLLP
178689 | 02.08.22 | Guard alert | Pick from Supplier
178722 | 19.08.22 | Chimney-Hindware | Pick from Supplier
178735 | 26.08.22 | Toughned Glass | Pick from Supplier
178740 | 29.08.22 | Cement Board | Work under process
178744 | 05.09.22 | Smile play | Pick from Supplier
178764 | 20.09.22 | MS Grills | Pick from SSLLP
178766 | 20.09.22 | Copper wire | Pick from SSLLP
178770 | 26.09.22 | CP Wall Mixture | Pick from SSLLP
178771 | 26.09.22 | Waste Coupling | Pick from SSLLP
178778 | 30.09.22 | Panel Doors | Pick from SSLLP
178779 | 04.10.22 | False Ceiling lights | Pick from SSLLP
178784 | 04.10.22 | Traffic Cone | Pick from SSLLP
178787 | 07.10.22 | Tan Brown Granite | Pick from SSLLP
178789 | 11.10.22 | Wires | Pick from SSLLP
178795 | 14.10.22 | Tandoor stone | Pick from Supplier
178799 | 19.10.22 | Aluminium Armoured Cable | Pick from Supplier
178800 | 19.10.22 | LED Street Lights | Pick from SSLLP
178801 | 20.10.22 | Kitchen Cabinate | Pick from SSLLP
178802 | 20.10.22 | RCC Jali | Pick from SSLLP