## Vista
Prepared by: | vanajakshi
Report Date | 26.10.2022
Site | Greenwood Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142188 | 07.09.2022 | Gas cylinder | Local Purchase
142272 | 13.10.2022 | Vertified tiles | po to be issue
142278 | 17.10.2022 | Electrical copper wires | PO:93061
142283 | 17.10.2022 | Cutting blades | Quotes to be receive
142284 | 17.10.2022 | Fire rated doors | po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
142075 | 15.07.2022 | Building block | Next week delivery
142115 | 2.08.2022 | Guard alert siren | Supplier Arranging Material
142121 | 3.08.2022 | Regal beige & urban wood dark floor tiles | Awaiting for arranging the material
142216 | 24.09.2022 | Kajariya dyna tiles | Awaiting for arranging the material
142218 | 28.09.2022 | Steel MS grills | Awaiting for arranging the material
142236 | 4.10.2022 | Doors & Hardware | Next week delivery
142238 | 4.10.2022 | Glass balcony railing | Supplier Arranging Material
142243 | 6.10.2022 | Plumbing CP material | Next week delivery
142245 | 6.10.2022 | CP Sanitary | Next week delivery
142260 | 9.10.2022 | Nitco bibliostiles | Awaiting for arranging the material
142275 | 14.10.2022 | concealed tank | Next week delivery
142279 | 17.10.2022 | electrical material | Next week delivery
142280 | 17.10.2022 | electrical material | Next week delivery
142286 | 17.10.2022 | Ultra sprinkle tiles | Delivered
142287 | 17.10.2022 | Malasian brown tiles | Delivered