## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-10-15
Site |  | GMR
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO not prepared 3 working days after requisition:
193769 | 2022-09-05 | Fire doors | Cancelled and issued another requisition
193772 | 2022-09-05 | UPVC Windows | PO 92165
193798 | 2022-09-05 | MS Grills | PO 91790
193827 | 2022-09-12 | Drilling machine rod cutting machine, cutting blade | Cancelled another requisition issued Req no 193877
193931 | 2022-09-13 | Panel doors and beeding | PO 92037
193840 | 2022-09-14 | CPVC Material | PO 92274
193839 | 2022-09-14 | Plumbing material | PO 92154
193843 | 2022-09-14 | Plumbing material | PO 92157
193844 | 2022-09-14 | CPVC Material | PO 92153
193846 | 2022-09-14 | CP Extension nipple | PO 92152
List of requisitions Where PO/WO is prepared and items have not received at site
208009 | 2022-10-08 | MS Grills | Co ordinate with purushotham for delivery
208022 | 2022-10-10 | electrical wires and switches | Deliverd
208036 | 2022-10-11 | electrical wires and switches | Deliverd
208037 | 2022-10-11 | Electrical wires | Deliverd
208045 | 2022-10-12 | CP Material | Pick up from SSLLP
193505 | 2022-07-21 | MS Grills | Co ordinate with purushotham for delivery
193565 | 2022-08-02 | Guard alert siren | Pick up from SSLLP
193595 | 2022-08-06 | Plumbing material | Cancel this and issue a new requisition for the same material if you require
193606 | 2022-08-08 | Hardware material | Cancel this and issue a new requisition for the same material if you require
193621 | 2022-08-10 | Panel doors | Deliverd
193644 | 2022-08-13 | CP Material | Deliverd
193699 | 2022-08-20 | PVC matrial | Deliverd
193779 | 2022-09-05 | CPVC material | Deliverd
193784 | 2022-09-07 | tan brown granite | Deliverd
193789 | 2022-09-09 | Electriacl material | Deliverd
193792 | 2022-09-09 | Panel doors and beeding | Deliverd
193794 | 2022-09-09 | Electrical material | Pick up from SSLLP
193809 | 2022-09-10 | CPVC material | Deliverd
193817 | 2022-09-10 | Plumbing material | Deliverd
193818 | 2022-09-10 | CPVC material | Deliverd
193820 | 2022-09-10 | Hardware material | Deliverd
193821 | 2022-09-10 | tan brown granite | Deliverd