## Vista
Prepared by: | Ramya
Report Date | 27-10-22
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
184575 | 2022-05-09 | Tiles nitco biblios country almond, chocolate, rosso | pick up from GMR
184617 | 2022-12-09 | Tiles ispira urbanwood dark | pick up from GMR
184657 | 2022-05-09 | Electrical copper wire | pick up from SSLLP
184675 | 2022-08-09 | Gunny bags & sponges | pick up from SSLLP
184679 | 2022-12-09 | Electrical copper wire | pick up from SSLLP
184682 | 23-09-22 | Macharla stone red & yellow chocolate colour | pick up from SSLLP
184691 | 23-09-22 | CP Sanitary | pick up from SSLLP
184692 | 2022-10-10 | CP Plumbing material | pick up from SSLLP
184693 | 23-09-22 | CP Plumbing material | pick up from SSLLP
184694 | 26-09-22 | UPVC Windows | deliverd
184697 | 26-09-22 | Tile grout cement and consumable | pick up from SSLLP
184698 | 2022-07-10 | Electrical copper wire | deliverd
184699 | 28-09-22 | Electrical copper wire | pick up from SSLLP
184700 | 28-09-22 | Electrical copper wire | pick up from SSLLP
184701 | 28-09-22 | Number plates & name plate | fallow up with supplier
184705 | 28-09-22 | Electrical copper wire | pick up from SSLLP
184706 | 30-09-22 | Eletrical aluminium service wire | pick up from SSLLP
184707 | 2022-03-10 | Electrical copper wire | pick up from SSLLP
184710 | 2022-03-10 | Panel doors & hardware material | pick up from SSLLP
184711 | 2022-03-10 | Panel doors & hardware material | pick up from SSLLP
184712 | 2022-04-10 | Panel doors & hardware material | pick up from SSLLP
184713 | 2022-08-10 | CP Plumbing material | pick up from SSLLP
184714 | 2022-10-10 | CP Sanitary plumbing material | pick up from SSLLP