## GVRC
Prepared by: |  | P.Prabhakar
Report Date |  | 2022-10-22
Site |  | GMR
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO not prepared 3 working days after requisition:
208096 | 2022-10-20 | Electrical material | PO 93257
208090 | 2022-10-19 | Vadila, tacoma | PO 93164
208081 | 2022-10-18 | Fire rated doors | Estimate to be prepared
208078 | 2022-10-17 | LED Tube lights | PO 93158
208077 | 2022-10-17 | LED Square sufrace lights | PO 93172
208074 | 2022-10-17 | LED Flood lights | PO 93171
208072 | 2022-10-17 | UPVC Windows | PO 93214
208006 | 2022-10-08 | Foam boards | Promotions to follow up
List of requisitions Where PO/WO is prepared and items have not received at site
208080 | 2022-10-18 | LED Flood lights | Deliverd
208073 | 2022-10-17 | Wall putty | Deliverd
208076 | 2022-10-17 | Scartch plaster | Collect from Graflex
208068 | 2022-10-17 | PVC Material | Collect from SSLLP
208060 | 2022-10-15 | Plumbing material | Collect from SSLLP
208047 | 2022-10-12 | Eelctrical material | Deliverd
208046 | 2022-10-12 | Eelctrical material | Deliverd
208045 | 2022-10-12 | CP Material | Collect from SSLLP
208044 | 2022-10-12 | CP Material | Collect from SSLLP
208024 | 2022-10-10 | Eelctrical material | Deliverd
208003 | 2022-10-04 | CP Material | Deliverd
193978 | 2022-09-30 | EWC | Deliverd
193976 | 2022-09-30 | Tan brown granite | Pick up from SOV
193913 | 2022-09-24 | Panel doors | Collect from SSLLP
193911 | 2022-09-24 | SS Number plates | Under procuction
193908 | 2022-09-24 | Vent cover, socket plug | Deliverd
193907 | 2022-09-24 | PVC Material | Deliverd
193881 | 2022-09-20 | Tan brown granite | Deliverd
193839 | 2022-09-13 | Panel doors | Deliverd
193800 | 2022-09-12 | UPVC Windlws | Under procuction
193821 | 2022-09-10 | Tan brown granite | Deliverd
193803 | 2022-09-09 | Tan brown granite | Collect from SOV
193801 | 2022-09-09 | UPVC Windlws | Under procuction
193795 | 2022-09-09 | UPVC Windlws | Under procuction
193671 | 2022-09-17 | Tan brown granite | Collect from SOV
193563 | 2022-08-02 | Guard siren alert | Pick up from SSLLP