## NE
Prepared by: | Ramya
Report Date | 31.10.22
Site | Nilgiri Estates
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
175525 | 19-08-22 | MS Grill | Pick up from SSLLP
175531 | 23-09-22 | Blinds | Follow up with supplier
175539 | 15-10-22 | Blins | Follow up with supplier
175543 | 19-10-22 | Floor tiles | Pick up from GMR
175544 | 25-10-22 | CP Fittings | Pick up from SSLLP
175545 | 25-10-22 | CP Fittings | Pick up from SSLLP