## Vista
Prepared by: | Ramya
Report Date | 2022-10-31
Site | MHPLSOV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
185316 | 17-09-22 | Electrical diesel generator | Under Rates negoation by procurement team
185317 | 18-10-22 | UPVC Windos | Under Rates negoation by procurement team
List of requisitions Where PO/WO is prepared and items have not received at site
185320 | 21-10-22 | LED Square surface | pick up from SSLLP