## Vista
Prepared by: | Ramya
Report Date | 31-10-22
Site | SOV-part -3
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
184617 | 2022-12-09 | Tiles ispira urbanwood dark | pick up from GMR
184657 | 24-09-22 | Electrical copper wire | pick up from SSLLP
184667 | 28-09-22 | Electrical copper wire | pick up from SSLLP
184682 | 2022-03-10 | Macharla stone red & yellow chocolate colour | fallow up with supplier
184691 | 2022-10-10 | CP Sanitary plumbing material | pick up from SSLLP
184692 | 2022-10-10 | CP Plumbing material | pick up from SSLLP
184693 | 2022-10-10 | CP Sanitary plumbing material | pick up from SSLLP
184697 | 2022-12-10 | Tile grout cement and consumable | pick up from SSLLP
184698 | 2022-12-10 | Electrical copper wire | pick up from SSLLP
184699 | 2022-12-10 | Electrical copper wire | pick up from SSLLP
184700 | 2022-12-10 | Electrical copper wire | pick up from SSLLP
184701 | 14-10-22 | Number plates & name plate | fallow up with supplier
184705 | 14-10-22 | Electrical copper wire | pick up from SSLLP
184707 | 15-10-22 | Electrical copper wire | pick up from SSLLP
184710 | 15-10-22 | Panel doors & hardware material | pick up from SSLLP
184711 | 15-10-22 | Panel doors & hardware material | pick up from SSLLP
184712 | 15-10-22 | Panel doors & hardware material | pick up from SSLLP
184713 | 15-10-22 | CP Plumbing material | pick up from SSLLP
184714 | 15-10-22 | CP Sanitary plumbing material | pick up from SSLLP
184718 | 20-10-22 | upvc windows | fallow up with supplier
184724 | 22-10-22 | CPVC Material | pick up from SSLLP
184727 | 22-10-22 | wall & floor tiles ultra sprinkle | pick up from SSLLP
184728 | 22-10-22 | Electrical copper wire | pick up from SSLLP
184729 | 22-10-22 | PVC Plumbing material | pick up from SSLLP
184730 | 22-10-22 | Electrical copper wire | pick up from SSLLP