## KNM
Prepared by: | Deepa
Report Date | 22.09.22
Site | GHT
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142188 | 07.09.22 | Gas cylinder | Local purchase by Raghu
142284 | 17.10.22 | Fire rated Door | Req sent to procurement team
List of requisitions Where PO/WO is prepared and items have not received at site
142075 | 15.07.22 | Building Blocks | Next Weak delivey
142216 | 24.09.22 | Kajariya dyna tiles | pick up from sslpp
142218 | 28.09.22 | Steel Ms grill | Under Fabrication
142235 | 04.10.22 | upvc doors windows | Next Weak delivered
142236 | 04.10.22 | Panel doors | pick up from Ssllp
142238 | 04.10.22 | Glass balcony railing | work under progress
142243 | 06.10.22 | plumbing cp material | pick up from ssslpp
142245 | 06.10.22 | Cp sanitary | Next Weak delivery
142260 | 09.10.22 | Nitco bilblios tiles | Delivery in 2 days
142275 | 14.10.22 | concealed tank | Delivered
142278 | 17.10.22 | Electrical copper wires | Next Weak Deivery
142283 | 17.10.22 | cutting blades | Delivered
142293 | 20.10.22 | Wall tiles | pick up from sslpp
142296 | 22.10.22 | clam shell cards | Next Weak delivery
142297 | 22.10.22 | Led tube light | Delivered