## Vista
Prepared by: | Vanajakshi
Report Date | 12.11.2022
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
|  | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
95226 | 21.10.2022 | MS L angle | Next week delivery
95221 | 21.10.2022 | MS Z angle templates | Next week delivery
95239 | 5.11.2022 | Doors and hardware | Next week delivery
95240 | 7.11.2022 | Tiles | Next week delivery
95241 | 9.11.2022 | Tilegrout white | Next week delivery
95243 | 9.11.2022 | Rigid pipe | Next week delivery