## KNM
Prepared by: | Deepa
Report Date | 15.11.22
Site | GHT
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142284 | 17.10.22 | Fire rated Door | Req sent to procurement team
142350 | 08.11.22 | Armored cables | material is delivered
List of requisitions Where PO/WO is prepared and items have not received at site
142216 | 24.09.22 | Kajariya dyna tiles | pick up from Gmr
142218 | 28.09.22 | Steel Ms grill | Under Fabrication
142235 | 04.10.22 | upvc doors windows | delivered
142236 | 04.10.22 | Panel doors | pick up from Ssllp
142260 | 09.10.22 | Nitco bilblios tiles | Next weak delivery
142272 | 10.10.22 | Vitrifies tagus tile | pick up from Gmr
142296 | 22.10.22 | clam shell cards | Next weak delivery
142300 | 25.10.222 | Panel doors | pick up from Ssllp
142302 | 25.10.22 | luna wall tiles | pick up from Gmr
142310 | 29.10.22 | Regal beige & urban wood dark tiles | Pick up from GMr
142314 | 31.10.22 | blacowhiten & black berry | pick up from Gmr
142315 | 31.10.22 | luna wall tiles | pick up from Gmr
142316 | 31.10.22 | Ultrabsprinkle tiles | pick up from Gmr
142327 | 02.11.22 | shabad stone | Next weak delivery
142330 | 03.11.22 | ISMB & L anles | Next weak delivery
142343 | 07.11.22 | Curb stone | Delivered by tomorrow