## NE
Prepared by: | K Mounika
Report Date | 15-11-22
Site | Nilgiri Estates
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
175525 | 19-08-22 | MS Grill | Pick up from SSLLP
175531 | 23-09-22 | Blinds | Follow up with supplier
175539 | 15-10-22 | Blinds | Follow up with supplier
175543 | 19-10-22 | Floor tiles | Pick up from GMR
175545 | 25-10-22 | CP sanitary | Pick up from SSLLP
175548 | 2022-04-11 | CP sanitary | Pick up from SSLLP