## Vista
Prepared by: | vanajakshi
Report Date | 23.11.2022
Site | Dr.Nrk Biotech
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186438 | 3.11.2022 | FRP Tadaka | Estimation sent to MD'S approval
List of requisitions Where PO/WO is prepared and items have not received at site
186432 | 22.10.2022 | Coupler | Next Week Delivery
186427 | 18.10.2022 | ISMB | cancelled .Still,Supplier not supplied this material to site