## KNM
Prepared by: | Deepa
Report Date | 23.11.22
Site | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178801 | 20.10.22 | kitchen cabinets- Laminateds | Cancelled
List of requisitions Where PO/WO is prepared and items have not received at site
178477 | 31.03.22 | Toughened Glass | Next weak delivery
178722 | 19.08.22 | chimney -Hindware | Cancelled
178735 | 26.08.22 | Toughened Glass | Next weak delivery
178740 | 29.08.22 | Cement Fiber Board | Next weak delivery
178744 | 05.09.22 | Smile play | Next weak delivery
178764 | 20.09.22 | Ms Grill | Next weak delivery
178783 | 04.10.22 | Boom barrier | Next weak delivery
178787 | 07.10.22 | Tan brown Granite | Next weak delivery
178798 | 18.10.22 | Ms Grill | Next weak delivery
178813 | 31.10.22 | Steel Railing | Next weak delivery
178820 | 05.11.22 | Tan brown Granite | Next weak delivery
178831 | 11.11.22 | Copper wires | Next weak delivery
178832 | 12.11.22 | False ceiling Heights | Next weak delivery
178833 | 17.11.22 | Cpvc Elbow | Delivered