## Sheet1
Prepared by: | Venkateshwarlu.P
Report Date | 2022-11-24
Site | GMR
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
208302 | 18.11.22 | 7.5hp Submersible Pump | Requisitions Wrong
208292 | 17.11.22 | Glass Balcany Railing | Po done
208291 | 17.11.22 | Tiles | Po done
208290 | 17.11.22 | Tiles | Po done
208286 | 15.11.22 | Alu glass doors | Po done
208278 | 15.11.22 | Pannal Doors | Po done
208266 | 14.11.22 | MS Pipes | Po done
208274 | 12.11.22 | Nylon Rope | Cash purchase done by raghu
208236 | 09.11.22 | Earthing Strip | Requisitions Canselled by MD
208192 | 04.11.22 | Norice Board | Folow up with Pramotion team
List of requisitions Where PO/WO is prepared and items have not received at site
Req.No | Req.Date | Item Description | Details of discussion with supplier
208288 | 16.11.22 | Tile Grout | Delivered by tommatow
208285 | 16.11.22 | Sink with Drain Board | Delivery on Monday
208281 | 15.11.22 | Electrical Wires | Delivery on Monday
208279 | 15.11.22 | Tan brown granite | Material Delivered
208262 | 12.11.22 | Electrical Wires | Delivery on Monday
208248 | 10.11.22 | Electrical Wires | Delivery on Monday
208244 | 09.11.22 | Pannel doors | Delivery by next week
208243 | 09.11.22 | Electrical Wires | Delivery on Monday
208239 | 09.11.22 | Cp Material | Material Delivered
208226 | 09.11.22 | Plumbing Material(Eco Drain) | Delivery by tuesday
208225 | 09.11.22 | MS Squire Bar | Material Delivered
208219 | 08.11.22 | Tan brown granite | Material Delivered
208204 | 05.11.22 | Tan brown granite | Material Delivered
208181 | 2.11.22 | Anchor Bolts | Material Delivered
208169 | 31.10.22 | Tan brown granite | Material Delivered
208164 | 29.10.22 | Electrical Wires | Delivery on Monday
208159 | 29.10.22 | Octogonal poles | Material Delivered
208156 | 27.10.22 | Cpvc Tank Nipple | Material Delivered
208121 | 26.11.22 | Pvc Strip Connectors | Next Monday Delivered
208112 | 22.10.22 | Pannal Doors Beeding | Next week Delivered
208101 | 20.10.22 | Loft Tank & Cpvc Reducer | Material Delivered
193994 | 03.10.22 | Breath Analyzer | Purchase by raghu local purchase
193881 | 20.09.22 | Tan brown granite | Material Delivered