## NE
Prepared by: | K Mounika
Report Date | 24-11-22
Site | Nilgiri Estates
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
175525 | 19-08-22 | MS Grill | next week delivery
175543 | 19-10-22 | Tiles | next week delivery
175547 | 2022-04-11 | CP sanitary | Next week delivery
175548 | 2022-04-11 | CP sanitary | Pick up from SSLLP
175551 | 16-11-22 | Birla cement putty | Delivered
175550 | 16-11-22 | MS Grill | Next week delivery