## KNM
Prepared by: | Kavitha
Report Date | 2021-08-10
Site | Aedis Developers LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
100504 | 28-09-2021 | Cylindrical locks | pick up from ssllp
100503 | 25-09-2021 | White cement | pick up from ssllp
100500 | 22-09-2021 | Armoured cable | Follow up with suppleir
100499 | 22-09-2021 | Electrical items | pick up from ssllp
100498 | 22-9-2021 | Switches | pick up from ssllp
100497 | 22-09-2021 | Electrical wires | pick up from ssllp
100492 | 20-9-2021 | GI tee | Material is ready pick up from supplier
100490 | 18-09-2021 | MI Cemeras | Follow up with suppleir
100487 | 15-09-2021 | Man hole covers | Follow up with suppleir
100484 | 14-9-2021 | MS window grills | pick up from ssllp
100473 | 2021-06-09 | Steel sink | Prtly deliverd, balance to be pick from SSLLP
100467 | 2021-02-09 | Bathroom tiles | pick up from ssllp
100457 | 27-08-2021 | False ceiling | Follow up with suppleir
100449 | 17-08-2021 | Doors and hardware | Follow up with suppleir
100437 | 2021-06-08 | Panel doors | Prtly deliverd, balance to be pick from SSLLP
100436 | 2021-02-08 | Electrical wires | Prtly deliverd, balance to be pick from SSLLP
100430 | 28-7-2021 | RO Plant | Follow up with suppleir
100429 | 26-07-2021 | PVC coupling | Prtly deliverd, balance to be pick from SSLLP
100403 | 2021-03-07 | Bathroom tiles | Prtly deliverd, balance to be pick from MPL | MPL