## KNM
Prepared by: | Deepa
Report Date | 01.12 .22
Site | GHT
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142284 | 17.10.22 | Fire rated Door | follow up to procurement team
142294 | 20.10.22 | Modular kitchen work order | follow up to procurement team
142376 | 19.11.22 | Fire rated doule leaf door with glass | follow up to procurement team
142386 | 21.11.22 | Plumbing pvc material | po issue 94467
142389 | 22.11.22 | Bath room wall tiles | po issue 94269
List of requisitions Where PO/WO is prepared and items have not received at site
142218 | 28.09.22 | Steel Ms grill | Under Fabrication
142235 | 04.10.22 | upvc doors windows | delivered
142238 | 04.10.22 | Glass balcony railong | Delivered
142260 | 09.10.22 | Nitco bilblios tiles | Next weak delivery
142272 | 10.10.22 | Vitrifies tagus tile | pick up from Gmr
142300 | 25.10.222 | Panel doors | pick up from Ssllp
142302 | 25.10.22 | luna wall tiles | pick up from Gmr
142310 | 29.10.22 | Regal beige & urban wood dark tiles | Pick up from GMr
142314 | 31.10.22 | blacowhiten & black berry | pick up from Gmr
142315 | 31.10.22 | luna wall tiles | pick up from Gmr
142331 | 03.11.22 | CC hume pipes | Delivered
142338 | 04.11.22 | Panel doors | Next weak delivery
142349 | 08.11.22 | Coffee powder | Next weak delivery
142357 | 12.11.22 | Panel doors | Next weak delivery
142358 | 12.11.22 | Ms grill | Next weak delivery
142370 | 16.11.22 | Electrical pipes | Delivered
142372 | 17.11.22 | Cpvc material | Delivered
142374 | 18.11.22 | Plumbing cpvc | Delivered
142378 | 19.11.22 | HDPE pipe | Delivered
142380 | 21.11.22 | Monoblock pump | Delivered