## KNM
Prepared by: | Deepa
Report Date | 01.12.22
Site | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178842 | 20.10.22 | kitchen cabinets | follow up to procurement team
List of requisitions Where PO/WO is prepared and items have not received at site
178477 | 31.03.22 | Toughened Glass | Next weak delivery
178744 | 05.09.22 | Smile play | Next weak delivery
178764 | 20.09.22 | Ms Grill | Next weak delivery
178783 | 04.10.22 | Boom barrier | Delivered
178787 | 07.10.22 | Tan brown Granite | Next weak delivery
178798 | 18.10.22 | Ms Grill | Next weak delivery
178813 | 31.10.22 | Steel Railing | Next weak delivery
178820 | 05.11.22 | Tan brown Granite | Next weak delivery
178834 | 17.11.22 | Ms Grill | Next weak delivery