## Sheet1
Prepared by: | Venkateshwarlu.P
Report Date | 2022-12-02
Site | GMR
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
208354 | 25.11.22 | Panel Doors and hardware material | Po Completed
208299 | 18.11.22 | MS Aldrop | Cash Purchase By Raghu Today
208014 | 08.10.22 | GI Universal clamps | Po to issue
List of requisitions Where PO/WO is prepared and items have not received at site
Req.No | Req.Date | Item Description | Details of discussion with supplier
208347 | 23.11.22 | Wall Plug , SS Screws | Delivered By 05.12.22
208332 | 22.11.22 | Flexible Pipe | Material delivered
208331 | 22.11.22 | Alu.Armed cable | Its delevered next Week No Stock at supplie
208330 | 22.11.22 | A1 Service Cable | Material delivered
208329 | 22.11.22 | Chimney,HoB Hindware | Material delivered
208328 | 22.11.22 | Electrical Wires | Delivered By 05.12.22
208326 | 22.11.22 | Electrical Wires | Delivered By 05.12.22
208325 | 21.11.22 | GI Flat Patty | Material delivered
208313 | 19.11.22 | Electrical Wires | Delivered By 05.12.22
208306 | 19.11.22 | Anchor Bolt | Ready stock at supplier please send vehicle
208296 | 17.11.22 | Cp Material | Part Delivered, Part Next week
208295 | 17.11.22 | Electrical Wires | Part Delivered, Part Next week
208285 | 16.11.22 | SS Sink | Stock Recieves at SSLLP by 05.12.22
208278 | 15.11.22 | Panel Doors and hardware material | Stock Recieves at SSLLP by next week
208244 | 9.11.22 | Panel Doors and hardware material | Stock Recieves at SSLLP by next week
208268 | 05.11.22 | ISMB | Its delivered By Saterday
208209 | 05.11.22 | Electrcal digital Starter | Its Delivered By Monday
208181 | 02.11.22 | Anchor Bolt(pin Type) | Ready stock at supplier please send vehicle
208169 | 31.10.22 | tan brown granite | Material delivered
208163 | 29.10.22 | Electrical Wires(B&R) | Material delivered
208156 | 27.10.22 | Cpvc Tank Nipple | Ready stock at supplier,delivered by saterday
208131 | 26.10.22 | Electrical GI Strip | Ready stock at supplier,delivered by saterday
208112 | 22.10.22 | Panel Doors and hardware material | Stock Recieves at SSLLP by next week
208014 | 08.10.22 | Plumbing GI Material | Ready stock at supplier,delivered by saterday